# Executive Summary

Brightline Insurance engaged us to redesign its claims intake process. Our recommended changes would cut average claims processing time from 14 days to 6 days, a 57% reduction.

# Situation and Objectives

Brightline's claims intake process relies on manual document review and a legacy workflow system. Customer satisfaction scores have declined as processing times have grown. The objective of this engagement was to identify root causes of delay and recommend a redesigned process.

# Analysis

We mapped the end-to-end claims process across 200 sampled claims and identified three bottlenecks: manual document classification (accounting for 4 of the 14 days), sequential rather than parallel adjuster review (3 days), and a batch-processed approval queue that only runs twice daily (adding up to 1 day of pure queue time). Based on this analysis, an automated intake and parallel-review redesign would reduce average cycle time to approximately 8 days.

# Recommendations

We recommend Brightline implement automated document classification using OCR-based triage, move to parallel adjuster review for claims under $10,000, and move the approval queue to continuous processing.

# Implementation Roadmap

Phase 1 (Months 1-2): deploy automated document classification. Phase 2 (Months 3-4): pilot parallel review with two adjuster teams. Phase 3 (Months 5-6): roll out continuous approval processing and retire the legacy batch queue.